## Velocity Calculator Solution
Category | Description | Adjustment | Comments | Story Points
Last Sprint Velocity | Last Sprint Story Point Forecast | Data Entry | 8 Story Points Planned | 8
| Story Points Completed | Data Entry | 7 Completed | 7
| Effectiveness Percentage | Divide C3/C2 | 7/8 | 87.5%
| Current Sprint Baseline | C3 | Story Points Completed 7 | 7
Improvements | Improved Team Skills | Improved Production Percentage | Complete Training +10% | 7.7
| Increased Resources | % Increase in Resources | Added New AI Specialist +15% | 8.855
| Team Morale Boost | Improved Production Percentage | None
| Process Optimization | Improved Production Percentage | Estimated +5% | 9.2978
| Risk Exposure Reduction | Risk Factors Eliminated | Reduce workarounds by 10% | 10.2275
Deductions | Lost Key Team Member | % Decrease in Resources | None
| New Risk Identified | % Impact on Story Points | None
| New Technical Debt | Story Points Required to Fix | None
| Unplanned Work/Scope Creep | % Production Decrease to Address | None
| Integration Delays | % Production Decrease to Address | 5% Time Impact | 9.7161
Updated Velocity | Total Adjusted Velocity | Calculated | Round Up or Down | 9.7161