## Planning Solution
Release Planning
Sprint | User Story Backlog | Priority | Dependencies
1 | 001 | 1 | None
1 | 003 | 2 | None
2 | 002 | 3 | User Stories 001 and 003
2 | 004 | 4 | User Story 002
2 | 005 | 5 | User Story 002
2 | 007 | 6 | User Story 004 and 005
3 | 006 | 7 | User Story 007
3 | 008 | 8 | User Story 007

## Network Diagram Solution
Launch Plan for: Product ABC
Sprint 1 | Sprint 2 | Sprint 3
User Story Backlog
User Story 001
User Story 002
User Story 003
User Story 004
User Story 005
User Story 006
User Story 007
User Story 008