## Sprint Velocity Solution
Category | Description | Adjustment | Comments | Story Points
Last Sprint Velocity | Last Sprint Story Point Forecast | Data Entry | 18 Story Points Planned | 18
| Story Points Completed | Data Entry | 17 Completed | 17
| Effectiveness Percentage | Divide C3/C2 | 17/18 | 94.44%
| Current Sprint Baseline | C3 | Story Points Completed 17 | 17
Improvements | Improved Team Skills | Improved Production Percentage | Complete Training +15% | 19.55
| Increased Resources | % Increase in Resources | New Test Equipment +5% | 20.5275
| Team Morale Boost | Improved Production Percentage | N/A | 20.5275
| Process Optimization | Improved Production Percentage | N/A | 20.5275
| Risk Exposure Reduction | Risk Factors Eliminated | Reduce workarounds by 5% | 21.5539
Deductions | Lost Key Team Member | % Decrease in Resources | N/A | 21.5539
| New Risk Identified | % Impact on Story Points | N/A | 21.5539
| New Technical Debt | Story Points Required to Fix | 1 Story Point to Fix | 20.5539
| Unplanned Work/Scope Creep | % Production Decrease to Address | None | 20.5539
| Integration Delays | % Production Decrease to Address | 5% Time Impact | 20.3483
Updated Velocity | Total Adjusted Velocity | Calculated | Round Up or Down | 20.3483