## Planning Template
Release Planning
Sprint | User Story Backlog | Priority | Dependencies

## Network Diagram Template
Launch Plan for:
Sprint 1 | Sprint 2 | Sprint 3
User Story Backlog
User Story 001
User Story 002
User Story 003
User Story 004
User Story 005
User Story 006
User Story 007
User Story 008

## Planning Example
Release Planning
Sprint | User Story Backlog | Priority | Dependencies
1 | 001 | 1 | None
1 | 002 | 2 | None
1 | 003 | 3 | User Stories 001 and 002
2 | 004 | 4 | User Story 3
2 | 005 | 5 | User Story 4
3 | 007 | 6 | User Story 5
3 | 006 | 7 | User Story 6
3 | 008 | 8 | User Story 6
Note on D5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @ID: Should the value in this cell be “User Stories 1 and 2”?

## Network Diagram Example
Launch Plan for: Product ABC
Sprint 1 | Sprint 2 | Sprint 3
User Story Backlog
User Story 001
User Story 002
User Story 003
User Story 004
User Story 005
User Story 006
User Story 007
User Story 008