## Sprint Velocity Calculator
Category | Description | Adjustment | Comments | Story Points
Last Sprint Velocity | Last Sprint Story Point Forecast | Data Entry
| Story Points Completed | Data Entry
| Effectiveness Percentage | Divide C3/C2
| Current Sprint Baseline | C3
Improvements | Improved Team Skills | Improved Production Percentage
| Increased Resources | % Increase in Resources
| Team Morale Boost | Improved Production Percentage
| Process Optimization | Improved Production Percentage
| Risk Exposure Reduction | Risk Factors Eliminated
Deductions | Lost Key Team Member | % Decrease in Resources
| New Risk Identified | % Impact on Story Points
| New Technical Debt | Story Points Required to Fix
| Unplanned Work/Scope Creep | % Production Decrease to Address
| Integration Delays | % Production Decrease to Address
Updated Velocity | Total Adjusted Velocity | Calculated

## Velocity Calculator Example
Category | Description | Adjustment | Comments | Story Points
Last Sprint Velocity | Last Sprint Story Point Forecast | Data Entry | 30 Story Points Planned | 30
| Story Points Completed | Data Entry | 27 Completed | 27
| Effectiveness Percentage | Divide C3/C2 | 27/30 | 90%
| Current Sprint Baseline | C3 | Story Points Completed 27 | 27
Improvements | Improved Team Skills | Improved Production Percentage | Complete Training +5% | 28.35
| Increased Resources | % Increase in Resources | New Test Equipment +5% | 29.7675
| Team Morale Boost | Improved Production Percentage | Team Building Success +2% | 30.3629
| Process Optimization | Improved Production Percentage | Estimated +2% | 30.9701
| Risk Exposure Reduction | Risk Factors Eliminated | Reduce workarounds by 10% | 34.0671
Deductions | Lost Key Team Member | % Decrease in Resources | Lost Resource due to training 14.7% | 29.0593
| New Risk Identified | % Impact on Story Points | 3% Time Increase for mitigation | 28.1875
| New Technical Debt | Story Points Required to Fix | 2 Story Points to Fix | 26.1875
| Unplanned Work/Scope Creep | % Production Decrease to Address | None | 26.1875
| Integration Delays | % Production Decrease to Address | 1% Time Impact | 25.9256
Updated Velocity | Total Adjusted Velocity | Calculated | Round Up or Down | 25.9256